## Sheet1
Level 1 | Level 2 | Level 3 | Level 4
Internseek (Internship Application System) | 1.0 INITIATION | 1.1 Define Project Objectives
|  | 1.2 Identify Project Scope and Boundaries | 1.2.1 Determine core functionalities
1.2.2 Establish project constraints (time, cost, resources)
1.2.3 Define out-of-scope functionalities
1.2.4 Define project deliverables
|  | 1.3 Conduct Feasibility Study | 1.3.1 Analyze and assess the technical feasibility by evaluating the available tools and platforms
1.3.2 Assess resource feasibility, including budget and time
1.3.3 Assess market feasibility by analyzing the target market demand and competition
|  | 1.4 Identify Key Stakeholders | 1.4.1 Identify people involved in the system, directly affected individual, indirectly affected individual
1.4.2 Define the roles and responsibilities for every stakeholders
|  | 1.5 Perform Requirement Gathering | 1.5.1 Collect requirements from students and employers
1.5.2 Define initial success criteria
|  | 1.6 Plan User Engagement and Feedback Methods | 1.6.1 Define key milestones for user feedback
1.6.2 Determine the method for collecting feedback at the relevant milestones
| 2.0 PLANNING | 2.1 Create Project Schedule and Timeline | 2.1.1 Break down major milestones and deadlines
2.1.2 Establish task dependencies and key deliverables
|  | 2.2 Allocate Resources and Budget | 2.2.1 Define human resources and assign roles
2.2.2 Set and approve budget
|  | 2.3 Conduct Risk Assessment | 2.3.1 Identify potential project risks
2.3.2 Develop mitigation plans for high-priority risks
|  | 2.4 Arrange Priority Features and Requirements | 2.4.1 Rank features based on importance and feasibility
2.4.2 Align features with project objectives and stakeholder needs
2.4.3 Set clear acceptance criteria for each feature
|  | 2.5 Plan Development Tools and Frameworks | 2.5.1 Finalise backend and frontend frameworks
2.5.2 Choose necessary databases and tools
|  | 2.6 Design System Architecture, Relevant Diagrams | 2.6.1 Create Entity-Relationship diagrams for database structure
2.6.2 Design Context Diagram, Use Case Diagram, Sequence Diagram, Activity Diagram
2.6.3 Create Use Case Description, Data Dictionary
2.6.4 Design the high-level architecture of system
|  | 2.7 Create prototype | 2.7.1 Design user interfaces using Figma
2.7.2 Link the relationship between each interface
| 3.0 EXECUTION | 3.1 Set Up Development Environment and Version Control | 3.1.1 Establish development environment and workspace configuration
3.1.2 Set up version control and repositories
|  | 3.2 Install Required Dependencies | 3.2.1 Configure environmental variables
3.2.2 Set up modules used in development
|  | 3.3 Implement Database | 3.3.1 Design and create database schemas
3.3.2 Connect relational database connections
|  | 3.4 Develop User Authentication and Access Control | 3.4.1 Implement login and registration functionality
3.4.2 Add session management and access level permissions
3.4.3 Implement password reset and account recovery
|  | 3.5 Design Frontend Layout and Navigation | 3.5.1 Develop UI Components Based on Prototype Design
3.5.2 Develop the User Interface Using Previously Developed Components
3.5.3 Define Navigation Flow and Structure, and Implement Navigation Logic
3.5.4 Design the Interface to Be Responsive
|  | 3.6 Develop Backend Functionalities and Key Features | 3.6.1 Set Up Database Models and Relationships
3.6.2 Implement the CRUD functionality in the controller
3.6.3 Define the corresponding routes for each CRUD operation
3.6.4 Define the task schedule to automatically update the internship posting status based on the posting’s start and end date
3.6.5 Implement a messaging feature to enable communication between students and employers.
| 4.0 EXECUTION & MONITORING | 4.1 Conduct Unit Testing for Individual Components | 4.1.1 Write and run test cases for core functionalities
4.1.2 Document test results and fix identified issues
|  | 4.2 Perform Integration Testing for Feature Interactions | 4.2.1 Test interdependencies among modules
4.2.2 Record and troubleshoot any integration issues
|  | 4.3 Conduct System Testing on Whole Application | 4.3.1 Run complete system tests to ensure full functionality
4.3.2 Conduct end-to-end testing across major user scenarios
|  | 4.4 Conduct User Acceptance Testing (UAT) | 4.4.1 Create Google Form for UAT Testing
4.4.2 Execute UAT with End-Users and Collect Detailed Feedback
4.4.3 Make improvements based on collected feedback
|  | 4.5 Execute Load and Performance Testing | 4.5.1 Test application response time under high load
4.5.2 Optimize code or queries to improve performance
| 5.0 CLOSING | 5.1 Conduct Usability Testing | 5.1.1 Conduct usability testing sessions with users
5.1.2 Collect qualitative and quantitative feedback from users
5.1.3 Implement improvements based on usability feedback
|  | 5.2 Deploy Final Version to Production | 5.2.1 Migrate system to live server and set up domain
5.2.2 Verify deployment setup and accessibility
|  | 5.3 Prepare Handover Documentation | 5.3.1 Compile project documentation
5.3.2 Archive code, assets, and resources in repository
5.4 Create User Manual and Support Documents
|  | 5.5 Gather Post-Implementation Feedback | 5.5.1 Monitor user experience and address issues
5.5.2 Document user suggestions for future maintenance
|  | 5.6 Perform Final Review and Close-Out Report | 5.6.1 Review project goals, outcomes, and any discrepancies
5.6.2 Generate project close-out report with lessons learned
5.7 Collect Final Sign-Off from Stakeholders
5.8 Formally Close Project